## Slide 1: Black art of software estimation You cannot predict nor control what you cannot measure Fenton and Pfleeger, „Software Metrics“, 2nd Edition
Josip Šaban, M. Sc. computing, MBA, PMP
Erste Group IT, Vienna
Meridian Data, Zagreb
www.linkedin.com/in/josipsaban
josip.saban@erstegroup.com
meridiandatasoftware@gmail.com

## Slide 2: About me
FER Zagreb ( 2004 ), Cotrugli MBA ( 2011 )
MC* ( SQL Server, Biztalk, Project Server, .NET ), MCT from 2012 until 2014
CompTIA Project+, PMP, Prince2 Foundation, ITIL Foundation
Coursera - finished 9 courses and 3 specializations (big fan)
Worked on vendor and client side, from startups to corporate sector, from operational to management roles
Currently working in IT department in Erste Group IT in Vienna
Also owner of sole proprietorship Meridian Data
Private interests include soccer, judging tennis and travelling

## Slide 3: Lecture name origin
Lecture name taken from one of the best books in the field
  MS Press - Software Estimation - Demystifying The Black Art
Other key books ( not many on this topic )
  Wiley & Sons - Software Measurement And Estimation - A Practical Approach
  J. Ross Publishing - Software Estimation Best Practices Tools Techniques - A Complete Guide For Software Project Estimators
  Springer - Software Cost Estimation Benchmarking and Risk Assessment
  Auberback - Software Sizing, Estimation, and Risk Management - When Performance Is Measured Performance Improves
  ISBSG - Practical Software Project Estimation - A Toolkit For Estimating Software Development

## Slide 4: About this lecture
Scenario one
  You are a software manager responsible for building a new system and you need to tell the sales team how much effort it is going to take and how soon it can be ready
Scenario two
  You are responsible for making a go/no-go decision on releasing either a new system or an upgrade to an existing system
How do you answer these questions and are you conﬁdent in your decisions?
Notes: Scenario one details:
- You have relatively good requirements (25 use cases). You have a highly motivated team of ﬁve engineers. They tell you they can have it ready to ship in four months. What do you say? Do you accept their estimate or not?
Scenario two details:
- You have looked at the data. It tells you that there are approximately eight defects per thousand lines of code left in the system. Should you say “yes” or “no”?

## Slide 5: Lecture motivation
This is a senior level lecture, technology agnostic
All too often, we are faced with situations where we could rely only on our intuition and gut feelings rather than managing by the numbers
We will discuss required tools, data, and quantative measurements to make these kinds of decisions in software projects

## Slide 6: Lecture motivation
Managing your software by the numbers enables you to have repeatable results and continuous improvement
Software engineers need to be skilled in estimation and measurement
  Understand the activities and risks involved in software development
  Predicting and controlling the activities
  Managing the risks
  Delivering reliably
  Managing proactively to avoid crises

## Slide 7: So let’s begin…from basics
What you measure is what you get.
R.S. Kaplan and D.P. Norton, “The balanced scorecard - measures that drive performance,” The Harvard Business Review, 1992.

## Slide 8: Introduction
To define an appropriate measurements program you need to answer the following questions
  Who is the customer for the metrics
  What are their goals with respect to the product, process, or resource under measurement
  What metrics, when collected, will demonstrate whether or not the goal has been or is being met
Notes: To define an aligned metrics program, it is critical to engage your “customer” as well as project/organizational staff who are knowledgeable in the object to be measured. So no matter which approach is used, identifying your customer and getting the affected stakeholders involved will be a common element.
- A common misstep is to select the metrics based on what data is available or what is of most interest to the metrics engineer. These metrics efforts tend to be doomed before they begin. It costs money and time to collect metrics. The metrics need to be valuable to whomever is asking for the work to be done—that is, the customer. Always begin with an understanding of who the customer is.

## Slide 9: Importance of estimations
During the planning phase of a project, it is necessary to make „first guess” about cost and time
Estimations are often the basis for the decision to start a project
Estimations are the foundation for project planning and for further actions
  Estimating is one of the core tasks of project management, but still considered as black magic!

## Slide 10: What do we get out of the estimate
Components
Size
Effort needed
Cost
Time
Risk
Data for future improvements

## Slide 11: Who measures
Recommended: Project Lead
  Person responsible for completion of estimated task
Often: You!

## Slide 12: Why do we measure
Estimation gives the Customer:
  Budget
  “Quote” to compare with
Estimation gives the Supplier:
  Budget
  Chance to evaluate risks/rewards of a project
  Way to keep track of progress
Why is this Important to You?
  It will be a part of your job as Software Engineers!

## Slide 13: When do we measure
Before Development
  When project is acquired from customer
  Following project Approval for internal projects
During Development
  Decreases Uncertainty (we discuss this later in more detail )
Estimating… After Development?
  Not as common - but very beneficial
  Compare actual cost size time to estimated values
  Improves knowledge for future estimations

## Slide 14: The Challenges
Many variables
  Sizing
  Development Environment
  Support Environment
  Staff (how much/how talented)
  Project „boredom”

## Slide 15: Components of an Estimation
Cost
  Personnel (in person days or valued in personnel cost)
    Person day: Effort of one person per working day
  Material (PCs, software, tools etc.)
  Extra costs (travel expenses etc.)
Development Time
  Project duration
  Dependencies
Infrastructure
  Rooms, technical infrastructure, especially in offshore scenarios
This lecture

## Slide 16: Estimating Development Time
Development time often estimated by formula
  Duration = Effort / People
Problem with formula, because:
  A larger project team increases communication complexity which usually reduces productivity
Therefore it is not possible to reduce duration arbitrarily by adding more people to a project
  Always valid: „Nine woman will not give birth in one month”

## Slide 17: Estimating Personnel Cost
Personnel type: Team leader, application domain expert, analyst, designer, programmer, tester…
  Cost rate: Cost per person per day
2 alternatives for cost rate:
  Single cost rate for all types (no differentiation necessary)
  Assign different cost rates to different personnel types based on experience, qualification and skills
Personnel cost: person days x cost rate.

## Slide 18: Challenge – size estimation
Not done as often as effort estimation
Why do we do it?
  Drives Scheduling and Cost Estimations
    Size -> Effort -> Cost
How do we size Software?

## Slide 19: Sizing – „the old way” – lines of code
How many lines are in STRNCAT function
Depends 
Notes: What number did you come up with? What rules did you decide to use? In experiments with students, the answers range from 11 to 19, with occasional counts over 100 if the data definitions are included. As with most everything, it depends on how you count and what the rules are. Did you count comment lines? Did you count lines with just a “g”? If instead, we have a well-specified model that tells us “the rules,” then, counting lines becomes simple, and the students all arrive at the same answer.

## Slide 20: Sizing – „the old way” – lines of code
Original method of estimating size
Program Size = LOC needed for functionality
How many LOC from the experiment?
  The world may never know…

## Slide 21: Calculating the LOC Estimate
      Alternative – Average between Min. and Max. LOC
Module 1 Estimated LOC |  |  |  | 
Functionality | Min LOC | Max. LOC | Likely LOC | Estimated LOC
F1 | 100 | 150 | 125 | 140
F2 | 95 | 120 | 105 | 105
TOTAL |  |  |  | 245

## Slide 22: LOC – Pros/Cons
Pros
  Beneficial for Real Time/Embedded Applications
  Can be used to create Historical data for future estimates
  Easy to count
Cons
  No defined “Line”
  Doesn’t promote code optimizations

## Slide 23: Estimating the effort
Person Hours/Months/[Unit of time]
Derives Schedule, Cost…

## Slide 24: Method - Analogy
How it’s done:
  Use knowledge of previous projects to come up with estimates
What is needed for success:
  Company must keep records
  Similar Projects must have been made

## Slide 25: Method - Analogy
Parameters for Analyzing
  Project Type
    Full life cycle
    Implementation
    Conversion
    Port
    Migration
  Client Information
    Application Domain
    Size of client’s organization
    Number of client locations
  Development Platform

## Slide 26: Analogy – Strengths/Weaknesses
Strengths:
  Reliable
  Intuitive
  Estimation Data can be purchased
Weaknesses
  Poor Record Keeping = bad estimates
  Not the best for new organizations
  Time consuming

## Slide 27: Method – Expert Judgement ( Delphi )
How it’s done:
  Work with Subject Matter Experts (SMEs) to formulate estimates
  If a small team of SMEs is used, a common estimate is derived
Works well because:
  No historical data needed
  If proper SME is chosen -
  Extremely accurate
  Quick
Inaccurate because:
  SME can be biased / inconsistent / overconfident

## Slide 28: Methods: Activity and Work Decomposition

## Slide 29: Methods: Activity and Work Decomposition
How it’s done:
  Outline the needed tasks involved for the project
  Should be done by person who ensures the tasks are accomplished.
  Use knowledge of needed work and skill set of the implementers to derive time estimates.
Pros:
  Estimator is knowledgeable of the work at hand
  No explicit sizing such as Lines of Code count is needed
Limitations:
  Subjective – accuracy is up to the estimator’s opinion
  No sizing

## Slide 30: Methods: Top-Down
How it’s done:
  Decomposition of system into smaller components
Works well because:
  Estimates are linked to requirements
Inaccurate when:
  Good requirements aren’t available
  Bias may lead to underestimation

## Slide 31: Methods: Bottom-Up
How it’s done:
  Individuals evaluate each component of the entire system.
  Sum to formulate project estimate
Works well because:
  Can be very accurate – detailed
  Builds responsibility
Issues:
  Time consuming process
  Details may not be available
  Bias can lead to underestimation
  Can miss integration costs

## Slide 32: Methods: Design To Cost
How it’s done:
  Work with SMEs to find out how much we can give the customer for given budget
Works well because:
  The price is right!
Issues:
  Need knowledge of functionality cost

## Slide 33: Estimating…Uncertainty?

## Slide 34: The Cone of Uncertainty
400% to 25% !?
  Current studies show closer to +100% / -50% at feasibility stage
  Strong tendency to underestimate

## Slide 35: Acknowledging Uncertainty
Alternatives to giving a single number
  Between X and Y person months
  X% chance it will be under Y person months
  Use the “pX” approach
    “X” = X% chance of NOT exceeding the estimate
    Example – You’re on a project and your estimate is 8 person months. You’ve researched that 10% of similar projects have been under budget.
      p10 estimate = 7 staff months – 10% chance of being under, 90% being over

## Slide 36: Dealing with Uncertainties
Communicate in a way that makes them known, such as the pX method.
Methodology > Gut Feelings
  Work pressure drives over confidence
Re-Estimate
  Feasibility Stage - Ball Park
  Requirements Stage – More Detailed
  Design Stage - Refined
Agile Environments:
  Expect higher uncertainty

## Slide 37: And now…Let’s get seriouS
The true measure of a man is what he would do if he knew he would never be caught
Lord Kelvin

## Slide 38: Methods: Parametric Models
How it’s done:
  Estimate by use of design parameters and mathematic formulas
Works well because:
  Fast
  Ease of use
  Can be re-useable
Issues:
  Models need to “fit the bill”
  Can end up being very inaccurate through poor choice of parameters

## Slide 39: COCOMO (COnstructive COst MOdel)
Developed by Barry Boehm in 1981
Also called COCOMO I or Basic COCOMO
Top-down approach to estimate cost, effort and schedule of software projects, based on size and complexity of projects
Assumptions:
  Derivability of effort by comparing finished projects (“COCOMO database”)
  System requirements do not change during development
  Exclusion of some efforts (for example administration, training, rollout, integration).

## Slide 40: Calculation of Effort
Estimate number of instructions
  KDSI = “Kilo Delivered Source Instructions”
Determine project complexity parameters: A, B
  Regression analysis, matching project data to equation
3 levels of difficulty that characterize projects – templates for companies that don’t have resources for their A/B calculations
  Simple project (“organic mode”)
  Semi-complex project (“semidetached mode”)
  Complex project (“embedded mode”)
Calculate effort
  Effort = A * KDSIB
Also called Basic COCOMO
Notes: A and B can be determined by a curve fit procedure (regression analysis), matching project data to the equation (this is how you calibrate your data to the Cocomo model)
But most organizations do not have enough data to perform such an analysis
So Boehm has identified three levels of difficulty that seem to characterize many software projects
A further COCOMO assumption:
1 staff month = 152 productive hours (8 hours per day, 19 days/month), (less weekends, holidays, etc.)
Simple: small developer groups work on a well known problem
Semi-complex: complexity between „simple“ and „complex“, either unknown problem or large group of developers
Complex: large groups of developers, Problem domain unknown
[PM] means „person months“
By using cost drivers, in many cases a more accurate estimate is possible

## Slide 41: Calculation of Effort in Basic COCOMO
Formula: Effort = A * KDSIB
  Effort is counted in person months: 152 productive hours (8 hours per day, 19 days/month, less weekends, holidays, etc.)
  A, B are constants based on the complexity of the project
Project Complexity | A | B
Simple | 2.4 | 1.05
Semi-Complex | 3.0 | 1.12
Complex | 3.6 | 1.20
Notes: A and B can be determined by a curve fit procedure (regression analysis), matching project data to the equation (this is how you calibrate your data to the COCOMO model). But most organizations do not have enough data to perform such an analysis
So Boehm has identified three levels of difficulty that seem to characterize many software projects
A further COCOMO assumption: 1 staff month = 152 productive hours
(8 hours per day, 19 days/month)
(less weekends, holidays, etc.)

## Slide 42: Calculation of Development Time
Basic formula: T = C * EffortD
  T = Time to develop in months
  C, D = constants based on the complexity of the project
  Effort = Effort in person months (see slide before)
Project Complexity | C | D
Simple | 2.5 | 0.38
Semi-Complex | 2.5 | 0.35
Complex | 2.5 | 0.32

## Slide 43: Basic COCOMO Example
Volume = 30000 LOC = 30KLOC
Project type = Simple
Effort = 2.4 * (30)1.05 = 85 PM
Development Time = 2.5 * (85)0.38 = 13.5 months
=> Avg. staffing: 85/13.5 = 6.3 persons
=> Avg. productivity: 30000/85 = 353 LOC/PM

## Slide 44: Other COCOMO Models
Intermediate COCOMO
  15 additional cost drivers ( parameters ) yielding a multiplicative correction factor
  Basic COCOMO is based on value of 1.00 for each of the cost drivers
Detailed COCOMO
  Multipliers depend on phase: Requirements; System Design; Detailed Design; Code and Unit Test; Integrate & Test; Maintenance

## Slide 45: Steps in Intermediate COCOMO
Basic COCOMO steps
  Estimate number of instructions
  Determine project complexity parameters: A, B
  Determine level of difficulty that characterizes the project
New step
  Determine cost drivers
    15 cost drivers c1 , c1 …. c15
Calculate effort
  Effort = A * KDSIB * c1 * c1 …. * c15
Notes: A and B can be determined by a curve fit procedure (regression analysis), matching project data to the equation
(this is how you calibrate your data to the Cocomo model)
But most organizations do not have enough data to perform such an analysis
So Boehm has identified three levels of difficulty that seem to characterize many software projects
A further COCOMO assumption:
1 staff month = 152 productive hours
(8 hours per day, 19 days/month)
(less weekends, holidays, etc.)
Simple: small developer groups work on a well known problem
Semi-complex: complexity between „simple“ and „complex“, either unknown problem or large group of developers
Complex: large groups of developers, Problem domain unknown
[PM] means „person months“
By using cost drivers, in many cases a more accurate estimate is possible

## Slide 46: Calculation of Effort in Intermediate COCOMO
Basic formula:
  Effort = A * KDSIB * c1 * c1 ….* c15
  Effort is measured in PM (person months, 152 productive hours (8 hours per day, 19 days/month, less weekends, holidays, etc.)
    A, B are constants based on the complexity of the project
Project Complexity | C | D
Simple | 2.4 | 1.05
Semi-Complex | 3.0 | 1.12
Complex | 3.6 | 1.20
Notes: A and B can be determined by a curve fit procedure (regression analysis), matching project data to the equation (this is how you calibrate your data to the COCOMO model). But most organizations do not have enough data to perform such an analysis
So Boehm has identified three levels of difficulty that seem to characterize many software projects
A further COCOMO assumption: 1 staff month = 152 productive hours
(8 hours per day, 19 days/month)
(less weekends, holidays, etc.)

## Slide 47: Intermediate COCOMO: 15 Cost drivers
Product Attributes
  Required reliability
  Database size
  Product complexity
Computer Attributes
  Execution Time constraint
  Main storage constraint
  Virtual Storage volatility
  Turnaround time
Personnel Attributes
  Analyst capability
  Applications experience
  Programmer capability
  Virtual machine experience
  Language experience
Project Attributes
  Use of modern programming practices
  Use of software tools
  Required development schedule
Rated on a qualitative scale between "very low" and "extra high„
Associated values are multiplied with each other

## Slide 48: COCOMO II
Revision of COCOMO I in 1997
Provides three models of increasing detail
  Application Composition Model
    Estimates for prototypes based on GUI builder tools and existing components
  Early Design Model
    Estimates before software architecture is defined
    For system design phase, closest to original COCOMO, uses function points as size estimation
  Post Architecture Model
    Estimates once architecture is defined
    For actual development phase and maintenance; Uses FPs or SLOC as size measure
Estimator selects one of the three models based on current state of the project

## Slide 49: COCOMO II
Targeted for iterative software lifecycle models
  Boehm’s spiral model
  COCOMO I assumed a waterfall model
    30% design; 30% coding; 40% integration and test
COCOMO II includes new costs drivers to deal with
  Team experience
  Developer skills
  Distributed development
COCOMO II includes new equations for reuse
  Enables build vs. buy trade-offs

## Slide 50: COCOMO II: Added Cost drivers
Development flexibility
Team cohesion
Developed for reuse
Precedent
Architecture & risk resolution
Personnel continuity
Documentation match life cycle needs
Multi-Site development

## Slide 51: Advantages of COCOMO
Appropriate for a quick, high-level estimation of project costs
Fair results with smaller projects in a well known development environment
  Assumes comparison with past projects is possible
Covers all development activities (from analysis to testing)
Intermediate COCOMO yields good results for projects on which the model is based

## Slide 52: Problems with COCOMO
Judgment requirement to determine the influencing factors and their values
Experience shows that estimation results can deviate from actual effort by a factor of 4
Some important factors are not considered:
  Skills of team members, travel, environmental factors, user interface quality, overhead cost

## Slide 53: Problems with COCOMO
Judgment requirement to determine the influencing factors and their values
Experience shows that estimation results can deviate from actual effort by a factor of 4
Some important factors are not considered:
  Skills of team members, travel, environmental factors, user interface quality, overhead cost

## Slide 54: Function Point Analysis
Developed by Allen Albrecht, IBM Research, 1979
Technique to determine size of software projects
  Size is measured from a functional point of view
  Estimates are based on functional requirements
Albrecht originally used the technique to predict effort
  Size is usually the primary driver of development effort
Notes:   Size is measured from a functional point of view, not from a task view. In that sense function point analysis focuses more on the functional model (requirements analysis) than on the task model (project management). In other words, estimates are based on the users view of the functionality , not the developers view.
  However, the types of functions that Albrecht had in mind were transactions in a functionally decomposed system. Whether function points can be used to count use cases is an open question.
  Function points are not a perfect measure of effort to develop an application or of its business value, although the size in function points is typically an important factor in measuring each. This is often illustrated with an analogy to the building trades. A three thousand square foot house is usually less expensive to build one that is six thousand square feet. However, many attributes like marble bathrooms and tile floors might actually make the smaller house more expensive. Other factors, like location and number of bedrooms, might also make the smaller house more valuable as a residence.
  Historical note (From Ray Boehm: http://ourworld.compuserve.com/homepages/softcomp/fpfaq.htm)
  In the late seventies, IBM felt the need to develop a language independent approach to estimating software development effort. It tasked one of its employees, Allan Albrecht, with developing this approach. The result was the function point technique. In the early eighties, the function point technique was refined and a counting manual was produced by IBM's GUIDE organization. The International Function Point Users Group (IFPUG) was founded in the late eighties. This organization produced its own Counting Practices Manual. In 1994, IFPUG produced Release 4.0 of its Counting Practices Manual.

## Slide 55: Function Point Analysis
Independent of
  Implementation language and technology
  Development methodology
  Capability of the project team
A top-down approach based on function types
  Three steps: Plan the count, perform the count, estimate the effort.

## Slide 56: Steps in Function Point Analysis
Plan the count
  Type of count: development, enhancement, application
  Identify the counting boundary
  Identify sources for counting information: software, documentation and/or expert
Perform the count
  Count data access functions
  Count transaction functions
Notes: Function Point Analysis is based on a functional decomposition of the system into input, transformation and output functions.
The Analysis consists of two steps: Planning the count, and performing the count.
A) Plan the Count. This step includes two steps: 1) determine the type of count, and 2) identify counting boundary. It also includes critical logistics around the identification of counting information.
There are three types of counts: development project counts, enhancement project counts and application counts. The development project count also yields the first application count for an application.
Identifying the counting boundary can be complicated. In some cases, changing the counting boundary will make it necessary to do a different type of function point count. For example, what appeared to be a development project count was actually an application count followed by an enhancement project count.
There are three sources for counting information: the system to be counted, its documentation and the system expert (Application domain or solution domain expert). These sources are in increasing order of value to the counting process. One can perform a system count only with access to the system (software): this is usually very time consuming. Counting from the documentation is usually fast if the documentation is complete and easy to understand: It never is! The system expert can walk you through the other information and answer questions as they arise during the count. In function point analysis it is important, to get a system expert assigned with the counter for the entire count. Identification of the appropriate system expert is not always easy. It also depends on the counting boundary. An expert for one component of an application may be unaware of the particulars of other components.
Nevertheless, the system expert is often the application domain expert or the software architect. It may also be an end user who is very familiar with the application. It is usually not the project manager. Interestingly enough, the project manager is usually more willing to work with you directly than to assign the system expert.
B) Do the Count:
1.Count data function types. Data functions are either accessing Internal Logical Files (ILFs) or External Interfaces Files (EIFs). The count of the ILFs and EIFs is done by examining the data model (E/R model or the attributes of the persistent objects in the object model) or by asking the system designer for the application’s main categories of persistent data. This count must be done before the transactions function types are counted, because the complexity of the transactions is dependent on the way the data access functions are identified.
2. Count the transaction function types. Transaction function types are External Inputs (EIs), External Outputs (EOs) or External Queries (EQs). This is typically the longest part of the count, and the part where the system expert's assistance really saves time. Complexity of each transaction is based, in part, on the number of data types it references. The system expert can usually make this determination without consulting any documentation.
3. Compute the Unadjusted function points based on weight factors shown on the next slide.
4.Next we assign rating values 0 to 5 to the so called GSC factors (general system complexity factors). There are 14 GSC factors
shown on the next slide.
5. We sum up all 14 weighted GSC factors and compute the so called valued added factor (VAF). The formula is
VAF = 0.65 + (sum of all GSC factors/100).
6. Next we calculate the Adjusted function points = VAF * Unadjusted function points
7. Then we make a estimation how many function points we can finish per day. This is also called as "Performance factor"･
8. On the basis of the performance factor we calculate the effort in Person Days.

## Slide 57: Steps in Function Point Analysis
Estimate the effort
  Compute the unadjusted function points (UFP)
  Compute the Value Added Factor (VAF)
  Compute the adjusted Function Points (FA)
  Compute the performance factor
  Calculate the effort in person days
Notes: Function Point Analysis is based on a functional decomposition of the system into input, transformation and output functions.
The Analysis consists of two steps: Planning the count, and performing the count.
A) Plan the Count. This step includes two steps: 1) determine the type of count, and 2) identify counting boundary. It also includes critical logistics around the identification of counting information.
There are three types of counts: development project counts, enhancement project counts and application counts. The development project count also yields the first application count for an application.
Identifying the counting boundary can be complicated. In some cases, changing the counting boundary will make it necessary to do a different type of function point count. For example, what appeared to be a development project count was actually an application count followed by an enhancement project count.
There are three sources for counting information: the system to be counted, its documentation and the system expert (Application domain or solution domain expert). These sources are in increasing order of value to the counting process. One can perform a system count only with access to the system (software): this is usually very time consuming. Counting from the documentation is usually fast if the documentation is complete and easy to understand: It never is! The system expert can walk you through the other information and answer questions as they arise during the count. In function point analysis it is important, to get a system expert assigned with the counter for the entire count. Identification of the appropriate system expert is not always easy. It also depends on the counting boundary. An expert for one component of an application may be unaware of the particulars of other components.
Nevertheless, the system expert is often the application domain expert or the software architect. It may also be an end user who is very familiar with the application. It is usually not the project manager. Interestingly enough, the project manager is usually more willing to work with you directly than to assign the system expert.
B) Do the Count:
1.Count data function types. Data functions are either accessing Internal Logical Files (ILFs) or External Interfaces Files (EIFs). The count of the ILFs and EIFs is done by examining the data model (E/R model or the attributes of the persistent objects in the object model) or by asking the system designer for the application’s main categories of persistent data. This count must be done before the transactions function types are counted, because the complexity of the transactions is dependent on the way the data access functions are identified.
2. Count the transaction function types. Transaction function types are External Inputs (EIs), External Outputs (EOs) or External Queries (EQs). This is typically the longest part of the count, and the part where the system expert's assistance really saves time. Complexity of each transaction is based, in part, on the number of data types it references. The system expert can usually make this determination without consulting any documentation.
3. Compute the Unadjusted function points based on weight factors shown on the next slide.
4.Next we assign rating values 0 to 5 to the so called GSC factors (general system complexity factors). There are 14 GSC factors
shown on the next slide.
5. We sum up all 14 weighted GSC factors and compute the so called valued added factor (VAF). The formula is
VAF = 0.65 + (sum of all GSC factors/100).
6. Next we calculate the Adjusted function points = VAF * Unadjusted function points
7. Then we make a estimation how many function points we can finish per day. This is also called as "Performance factor"･
8. On the basis of the performance factor we calculate the effort in Person Days.

## Slide 58: Function Types
Data function types
  # of internal logical files (ILF)
  # of external interface files (EIF)
Transaction function types
  # of external input (EI)
  # of external output (EO)
  # of external queries (EQ)
Calculate the UFP (unadjusted function points):
  UFP = a · EI + b · EO + c · EQ + d · ILF + e · EIF
a-f are unadjusted weight factors (see next slide)
Notes: There are two ways to count functions. The first way is the traditional Albrecht approach based on the analysis of transactions. The second way is based on the data modeling approach (E/R model).
To do the count, the FP counter has to do the following three steps:
1.Count data function types. Data functions are either accessing Internal Logical Files (ILFs) or External Interfaces Files (EIFs). The count of the ILFs and EIFs is done by examining the data model (E/R model or the attributes of the persistent objects in the object model) or by asking the system designer for the application’s main categories of persistent data. This count must be done before the transactions function types are counted, because the complexity of the transactions is dependent on the way the data access functions are identified.
2. Count the transaction function types. Transaction function types are External Inputs (EIs), External Outputs (EOs) or External Queries (EQs). This is typically the longest part of the count, and the part where the system expert's assistance really saves time. Complexity of each transaction is based, in part, on the number of data types it references. The system expert can usually make this determination without consulting any documentation.
3. Compute the Unadjusted function points based on weight factors shown on the next slide.

## Slide 59: Object Model Example
Customer
Name
Address
Amound Due
Item
Description
Pallets
Value
Storage Date
Owner
Storage Place
Place
Location
Space
owns
Stored at
1
1
*
*

## Slide 60: Calculate the Unadjusted Function Points
Weight Factors
Function Type
simple
average
complex
External Input (EI)
x
3
4
6
=
External Output (EO)
x
4
5
7
=
External Queries (EQ)
x
3
4
6
=
Internal Datasets (ILF)
x
7
10
15
=
Interfaces (EIF)
x
5
7
10
=
Unadjusted Function Points (UFP)
=
Number
Notes: After we have counted the ILF,EIF,EI and Eqs, we can compute the unadjusted function points UFP shown on this slide.
In function point analysis, each type of function (input, output, inquiry, file) is first assigned a 'complexity' weighting (simple, average, complex), suggesting that functional size is measured on an ordinal scale.
Next, a specific number of function points are allocated to each function depending on its type and complexity weighting. Within each set of functions belonging to a same type, the allocation of integer values to functions qualifies as an admissible transformation of scale.
The higher the complexity weighting, the more function points are allocated. For instance, external input functions get 3 function points if they are simple, 4 function points if they are of average complexity, and 6 function points if they are complex. Hence, within the class of input functions, one ordinal scale (simple, average, complex) is homomorphically transformed into another ordinal scale (3, 4, 6).
Next, the function points assigned to all individual functions are summed to arrive at the 'unadjusted function point count' for the entire system.
Note, that this operation is not meaningful given the ordinal scale type of the homomorphisms (one per function type) that allocate function point values to functions, but we don’t look into this argument here.

## Slide 61: Mapping Functions to Transaction Types
Add Customer
Change Customer
Delete Customer
Receive payment
Deposit Item
Retrieve Item
Add Place
Change Place Data
Delete Place
Print Customer item list
Print Bill
Print Item List
Query Customer
Query Customer's items
Query Places
Query Stored Items
External Inputs
External Outputs
External Inquiries

## Slide 62: Advantages of Function Point Analysis
Independent of implementation language and technology
Estimates are based on design specification
  Usually known before implementation tasks are known
Users without technical knowledge can be integrated into the estimation process
  Incorporation of experiences from different organizations
Easy to learn
  Limited time effort
Notes: Function Points measure software size independent of the programming language: no lines of code counting.
Function Points measure functionality by objectively measuring functional requirements.
Function Point Analysis is objective; Function Points are consistent, and Function Points are auditable.
Function Points are independent of technology. Function Points even apply regardless of design.

## Slide 63: Disadvantages of Function Point Analysis
Complete description of functions necessary
  Often not the case in early project stages -> especially in iterative software processes
Only complexity of specification is estimated
  Implementation is often more relevant for estimation
High uncertainty in calculating function points:
  Weight factors are usually deducted from past experiences (environment, used technology and tools may be out-of-date in the current project)
Does not measure the performance of people
Notes: Code reuse and external providers of software components are not considered
Function Points do not measure people directly.
Task planning and controlling is not possible (also: no breakdown to single project phases considered)
Function Points is a macro tool, not a micro tool.

## Slide 64: Online Availability of Estimation Tools
Basic and Intermediate COCOMO I (JavaScript)
  http://www1.jsc.nasa.gov/bu2/COCOMO.html
  http://ivs.cs.uni-magdeburg.de/sw-eng/us/java/COCOMO/index.shtml
COCOMO II (Unix, Windows and Java)
  http://sunset.usc.edu/available_tools/index.html
Function Point Calculator (Java)
  http://ivs.cs.uni-magdeburg.de/sw-eng/us/java/fp/

## Slide 65: Why Estimates Fail – A recap
Little / Misused historical data
  Record estimates + actual data
  Make sure data “fits the bill”
Over-Optimistic / Hopeful management
  Avoid gut feelings – use the methods
  Avoid over-confidence
Not using the estimate!
  Don’t Confuse targets with estimates
Not updating the estimate
  Acknowledge uncertainty in estimation
  Estimate often – it will become more accurate

## Slide 66: What’s next
Cost
  Personnel (in person days or valued in personnel cost)
    Person day: Effort of one person per working day
  Material (PCs, software, tools etc.)
  Extra costs (travel expenses etc.)
Development Time
  Project duration
  Dependencies
Infrastructure
  Rooms, technical infrastructure, especially in offshore scenarios
All of this + cost advanced topics

## Slide 67: L.W.F Factor

## Slide 68: Thank you for your time